## Sheet1
| Project Manager | Developer | UI/UX Designer | QA Engineer | Business Analyst | DevOps | Software Architect
Кіра
Максим
Настя

## Sheet2
# | Role | Responsible | Due date | Reg date | Due date | Status
1 | Project Manager | Max | Plan initial project setup, define goals, and allocate resources. | 2024-11-03 | 2024-11-03 | Done
2 | Business Analyst | Nastya | Gather detailed user requirements and refine specifications. | 2024-11-03 | 2024-11-03 | Done
3 | Developer | Nastya | Implement HTTP Requests and Data Parsing. | 2024-11-04 | 2024-11-22 | Done
4 | Developer | Kira | Develop Server Logic and Client Handling. | 2024-11-04 | 2024-11-22 | Done
5 | UI/UX Designer | Kira | Design wireframes and prototypes for the application. | 2024-11-22 | 2024-11-25 | Done
6 | QA Engineer | Nastya/Kira | Conduct unit testing for individual features of the server. | 2024-11-22 | 2024-11-25 | Done
7 | DevOps | Max | Automated testing and code integration on GitHub. | 2024-11-25 | 2024-11-25 | Done
8 | Software Architect | Kira | Define a modular structure for the application for scalability. | 2024-11-26 | 2024-11-26 | Done
9 | Developer | Max | Creation of a client with an interface and integration with the server. | 2024-11-26 | 2024-12-02 | Done
10 | QA Engineer | Max | Perform integration testing to validate system functionality. | 2024-12-02 | 2024-12-03 | Done
11 | Command | Nastya/Kira/Max | Coordinate with team members for project progress updates. | 2024-12-03 | 2024-12-04 | Done